## Sheet1
Meeting | Date | Overall | Greg | Nico | Alessandro | Tim | Olivier | Nick | Meeting Duration
1 | September 19th, 2024 | Disscused the overall work flow and task distributment. We will have the front end and back end teams. Aswell as the data management team. Each team will consist of 2 members. | Will be leading the backend team. Greg holds the greatest website coding knowledge therefore he will oversee all the coding and assure smooth sailing. | Will take care of the user minutes meeting times. Asses necessary scheduling for greater team coordination and team chemistry. As well as start learning how to code and join the front end team. | Take team leader for thefront end, aswell as increase his knowledge in css through educational videos for the purpose of creating a sophisticated frontend. | Wiil take the lead for the data management . Tim will compile the user stories and tasks so the team can have a clear and concise understanding of the mission | Will make a sprint planning page outline and will fill out the sprint planning page with respect to Nick & Tim's stories & task descriptions. Will also start watching educational videos on HTML programming to join along with the backend team. | Will take part in the data management team by compiling all of the user stories and taks to assure a proper targeted goal. Will also create the log format so that the team members can effectivley log all of their progress throught the project. | 3 hrs
2 | September 27th, 2024 | Assesed our progress on all the assigned tasks, gave more tasks and goals to the team members to effeciently complete sprint 1. | functionality of login, routing, and students account vs teacher account was created effectivley. Minor tweaks are needed towards the functionality of teams on the site. | obtained a foundation for coding in css. Can now work on frontend. Took in all members progress and updated the user minutes. | Created a working front login page that is aesthetically pleasing with css. Now needs to code the frontend of the register page and instructor dashboard | Created clear and concise user stories aswell as tasks. Will now brain storm using in class techniques for ways to achieve site goal criteria | Successfully create the foundation of the sprint plan. As well as added the user stories and further refined the goal criteria the team needs to meet. Learning how to further code in order to join the backend team. | Created clear and concise user stories aswell and further refined tasks. Created a better github structure and managed the project board for team organization. | 2.2 hrs
3 | Ocotober 3rd, 2024 | Did a retroactive review of the previous sprint and how we can improve our team work so that we are more efficient. | Great team leader on the back end, assured the tasks from the user stories were well broken into concise code that the other members of the back and can take (following simple chunks idea of scrum) | Great hybrid link between the datamanagment team and front end, assures good team communication and cooperation | Great Team leader for the front end, assured the tasks were small enough to be easily implmented and if they were, then implementation and distribution of the front end. | Great user stories that were well broken down into small enough chunks so that the coding teams could handle. | Was as fantastic hybrid between the data management team and the back end,this allowed for goodt team unification | Overlooked the teams coordination, made fantastic user stories and was a great medium for team coordination | 0.5 Hrs
4 | Ocotober 10th, 2024 | went over the user stories and everyones finalized work load for the entirety of the sprint. | started to create the foundation of the next sprints code, aswell as get code task distribution ready | Updated meeting minutes and was given his work load from Alessandro | started to create the foundation of the next sprints code, aswell as get code task distribution ready | Create the new sprint 2 user story plans and review his sprints and made sure they were well broken down for the coding team | Updated sprint planning page and was given his work load from Greg | Create the new sprint 2 user story plans and review his sprints and made sure the structure was followed for team organization | 1.2 Hrs
5 | October 19th, 2024 | check and updated everyone on their work status and level of completetion. | Started to complete all the tasks at hand and assured they followed the user stories aswell as assured backend coordination | started to complete his tasks and communicate with the olivier on backend for proper team communication | Started to complete all the tasks at hand and assured they followed the user stories aswell as assured frontend coordination | organized the team structure and further refined user story and tak, aswell as checked criteria the team needs to meet for sprint 2 | started to complete his tasks and communicate with the Nico on backend for proper team communication | organized the team structure and further refined user story and tak, aswell as checked criteria the team needs to meet for sprint 2 | 0.75 Hrs
8
9
10
11
12
13
14