## Sheet1
Work Log
Date | Team Member | Activity Description | Start Time | End Time | Time Spent (hrs) | Sprint
2024-09-16 | Nicholas Papamakarios | Created the Outline for user minutes for future organization | 18:00 | 18:45 | 0.75 | Sprint 1
2024-09-17 | Alessandro Condina | learned how to use gitHub and created new branch on Github (views) to work on the front end deliverables for Sprint1 | 17:00 | 18:00 | 1 | Sprint 1
2024-09-19 | Olivier Constanzo de Oliveira | Created the sprint planning appendix outline and set up my Git workflow on my pc | 17:00 | 18:30 | 1.5 | Sprint 1
2024-09-19 | Nicholas Papamakarios | Filled in the information on user minutes of each team members tasks and accomplishments for meeting 1 . | 19:00 | 20:00 | 1 | Sprint 1
2024-09-19 | Gregory Sacciadis | Created a basic skeleton for the web app (login page, get route, dependencies, .gitignore) | 20:00 | 20:30 | 0.5 | Sprint 1
2024-09-21 | Olivier Constanzo de Oliveira | Started a web development bootcamp to join the development team in sprint 2 | 13:00 | 14:00 | 1 | Sprint 1
2024-09-22 | Alessandro Condina | Styled the login and register pages and created a css directory for all of the style sheets + webdev research | 12:00 | 15:00 | 3 | Sprint 1
2024-09-22 | Gregory Sacciadis | Added a basic user model, a register page, and a home page. Post routes have been started. Implemented basic authorization routes with passport. | 12:00 | 14:30 | 2.5 | Sprint 1
2024-09-22 | Nicholas Gallacher | Created a README.txt file with a comprehensive description of the project, the first sprint activities, and team member's roles. | 18:00 | 19:30 | 1.5 | Sprint 1
2024-09-22 | Gregory Sacciadis | Added proper login and logout routes and started "isLogginIn" middleware (needs fixing) | 22:30 | 23:00 | 0.5 | Sprint 1
2024-09-23 | Alessandro Condina | Restructured the login page and generated a course roster with 90 random first and last names for testing the app. | 12:00 | 13:00 | 1 | Sprint 1
2024-09-23 | Nicholas Papamakarios | Started to learn how to code in CSS to eventually join the front end team | 19:00 | 21:00 | 2 | Sprint 1
2024-09-24 | Alessandro Condina | Merged main into views to work with new changes, and made some changes to register page css | 15:00 | 16:00 | 1 | Sprint 1
2024-09-24 | Gregory Sacciadis | Finished login, register, and logout logic. Reformatted login page & got rid of the unnecessary 'secret' routes and page | 13:00 | 14:30 | 1.5 | Sprint 1
2024-09-24 | Gregory Sacciadis | Added team model. Created instructor dashboard page with create empty teams & show teams functionality | 19:00 | 21:00 | 2 | Sprint 1
2024-09-25 | Alessandro Condina | Created an instructor dashboard and styled it, and worked on general structure of the web app. Merged more changes into Views branch and integrated them into frontend | 17:00 | 19:00 | 2 | Sprint 1
2024-09-26 | Gregory Sacciadis | Fixed instructor 'make teams' functionality. Instructors and students can now see their assigned teams. Fixed sign out bug. | 0:00 | 1:00 | 1 | Sprint 1
2024-09-26 | Nicholas Papamakarios | Filled in the information on user minutes of each team members tasks and accomplishments for meeting 1 . | 19:00 | 20:00 | 1 | Sprint 1
2024-09-26 | Nicholas Gallacher | Familiarized myself with the current codebase that was worked on by Gregory and Alessandro. | 17:00 | 18:00 | 1 | Sprint 1
2024-09-26 | Nicholas Gallacher | Reviewing some html, css and javascript to prepare for future development and code review. | 18:00 | 21:00 | 3 | Sprint 1
2024-09-26 | Olivier Constanzo de Oliveira | Discussed user stories and story points for sprint 1 | 16:00 | 17:00 | 1 | Sprint 1
2024-09-26 | Olivier Constanzo de Oliveira | Reviewed the codebase and ran the code with the necessary plugins for development | 17:00 | 19:00 | 2 | Sprint 1
2024-09-27 | Alessandro Condina | Created a team management, course roster, and structured the instructor dashboard. merged more changes and routed the newly created pages. Did research on webdev to learn more backend and frontend. | 14:00 | 18:00 | 4 | Sprint 1
2024-09-27 | Nicholas Papamakarios | Started to learn how HMTL in order to attain better understanding of the backend, which in turn allows for better intergration of the website. | 19:00 | 21:00 | 2 | Sprint 1
2024-09-28 | Timothy Moore | Developed GitHub workflow for creation and organization of user stories and tasks using GitHub Issues. Created the necessary labels and milestones in GitHub to better categorize issues. Restructured GitHub Projects agile board to better reflect scrum workflow. Assisted Nick G. with the creation of some user stories and tasks | 12:00 | 18:00 | 6 | Sprint 1
2024-09-28 | Nicholas Gallacher | Reorganized all work tasks done thus far and created user stories and tasks via GitHub issues. Created relevant acceptance criteria for each story, linked them to the tasks, assigned roles, and moved items to project board. | 18:00 | 23:00 | 5 | Sprint 1
2024-09-29 | Olivier Constanzo de Oliveira | Finished the sprint planning appendix to include the agreed upon story points and issues | 19:00 | 21:00 | 2 | Sprint 1
2024-09-29 | Timothy Moore | Added formatting to README.md and created GitHub Issue templates to streamline creation of new User Stories and tasks. Groomed user stories and task descriptions with Nick G. | 16:00 | 20:00 | 4 | Sprint 1
2024-10-05 | Nicholas Papamakarios | Updated teams meeting minutes for all team members and jotted team meetings | 14:00 | 15:00 | 1 | Sprint 2
2024-10-13 | Nicholas Gallacher | Estimated risk and story points for all previous user stories (sprint 1); updated github story format. | 17:00 | 18:00 | 1 | Sprint 2
2024-10-14 | Nicholas Gallacher | Reviewed user requirements for sprint 2; created user stories with descriptions, priority/risk levels, and story points; created relevant dev tasks and grouped them under respective user stories; added/updated GitHub issues according to template. | 18:00 | 21:00 | 3 | Sprint 2
2024-10-22 | Gregory Sacciadis | Added search students functionality, as well as the option to import a student roster csv and create teams based on that | 20:00 | 21:45 | 1.75 | Sprint 2
2024-10-25 | Olivier Constanzo de Oliveira | Pair programmed with Greg to implement get and post routes for student assessment funtionality to create evaluations in database | 16:00 | 17:25 | 1.4167 | Sprint 2
2024-10-25 | Gregory Sacciadis | Pair programmed with Olivier to implement get and post routes for student assessment funtionality to create evaluations in database | 16:00 | 17:25 | 1.4167 | Sprint 2
2024-10-26 | Alessandro Condina | added html and css for navbar and peer assessment | 20:00 | 22:00 | 2 | Sprint 2
2024-10-27 | Alessandro Condina | Paired programming with nico, finishing up the frontend | 13:00 | 17:30 | 4.5 | Sprint 2
2024-10-27 | Nicholas Papamakarios | Pair programmed with alessandro to implement print 2 front end | 13:00 | 17:30 | 4.5 | Sprint 2
2024-10-27 | Nicholas Gallacher | Created 2 acceptance tests. | 18:00 | 20:00 | 2 | Sprint 2
2024-10-27 | Gregory Sacciadis | Fixed merge conflicts | 21:00 | 22:15 | 1.25 | Sprint 2
2024-10-27 | Olivier Constanzo de Oliveira | Updated descriptions to tasks in issues | 22:00 | 23:30 | 1.5 | Sprint 2
2024-10-27 | Timothy Moore | Researched CI/CD workflow setup for GitHub and options for Node.js automated testing that are simple to use. Selected Jest as the top candidate for automated testing. | 16:00 | 20:00 | 4 | Sprint 2
2024-10-29 | Timothy Moore | Created basic GitHub workflow YAML script for Node.js CI that is triggered upon pushes and pull requests to any branch. Built upon the script to checkout code to a GitHub workspace, install dependencies, and run a basic assertion test. | 11:45 | 17:00 | 5.25 | Sprint 2
2024-10-30 | Timothy Moore | Reworked the testing models to be automated with Jest. Debugged issues with open handles revealed by Jest tests. Added basic test for the /register GET route. Will add more comprehensive route testing in the future. | 19:30 | 23:30 | 4 | Sprint 2
2024-10-31 | Timothy Moore | Added Jest tests for middleware function validation. | 11:00 | 13:00 | 2 | Sprint 2
95.3333