## Sprints
Sprint 1
Issue # | User story/Task title | Associated tasks/Task description | Story points (1,2,3,5,8,13) / Time estimate | Priority (LOW, MED, HIGH) | Risk (LOW, MED, HIGH) | Assigned to | Sprint due
11 | US.01: Implement login page | -Create html login page, -Add login CSS styling, -Implement login page routes. | 5 | High | High, main page of the system | Alessandro, Gregory | 1
5 | Task.01.01: Create login html page | Add basic HTML elements: form for inputting login information and a link to the registration page. | 3h | High | High | Alessandro, Gregory | 1
6 | Task.01.02: Add login page CSS styling | Style the divs, form, body, and other miscellaneous elements. | 2h | Med | Med | Alessandro | 1
12 | Task.01.03: Implement login page routes | -Create the GET route to render the login page. -Create the POST route to handle authentication, redirecting the user to their respective dashboard upon success or back to the login page upon failure. | 4h | High | High | Gregory | 1
13 | US.02: Implement registration page | -Create html register page, -Add register CSS styling, -Implement register page routes, -Create user model. | 5 | High | High, key user features to be built upon later | Alessandro, Gregory | 1
14 | Task.02.01: Create register html page | Add basic HTML elements: form for inputting registration details and a link to the login page. | 2h | High | High | Alessandro, Gregory | 1
15 | Task.02.02: Add register page CSS styling | Style the divs, form, body, and other miscellaneous elements. | 2h | Med | Med | Alessandro | 1
16 | Task.02.03: Implement register page routes | -Create the GET route to render the login page. -Create the POST route to handle authentication, redirecting the user to their respective dashboard upon success or back to the login page upon failure. | 3h | High | High | Gregory | 1
17 | Task.02.04: Create user model | -Define the user schema with fields for username, password, and user type (student or instructor). -Ensure user passwords are securely hashed upon registration. -Associate each user with a unique ID to track them in the system. | 3h | High | High | Gregory | 1
[8 empty] | Sprint Velocity: | 10
Sprint 2
Issue # | User story/Task title | Associated tasks/Task description | Story points | Priority | Risk | Assigned to | Sprint due
Sprint 3
Issue # | User story/Task title | Associated tasks/Task description | Story points | Priority | Risk | Assigned to | Sprint due
Sprint 4
Issue # | User story/Task title | Associated tasks/Task description | Story points | Priority | Risk | Assigned to | Sprint due